## Sheet1
Deliverable |  | Resource Name | Projected resources needed | Amount of resource required in (hours) or (number of items) | Cost Breakdown | Cost
Tasks | Description
All | Laptops for work to be done on | Laptops | 4 laptops | 4 laptops | 4 $1000 laptops = 4 x $1000 | 4000
All | Microsoft 365 | Microsoft 365 | Microsoft 365 x 4 months x 4 members | Microsoft 365 x 4 months x 4 members | 4 4 month subscriptions to Microsoft 365 = 4 months x 4 users x $23.23 per user per month | 371.68
1 | Planning - Prepare meeting | Team members meeting (workshop) | 4 hours x 3 members | 4 hours x 3 members | 4 hours x $25 per member = 4 x $75 | 300
1.1 | Personas | Man Hours | 2 hours x 3 members | 2 hours x 3 members | 2 hours x $25 per member = 2 x $75 | 150
1.2 | Persona Review meeting | Team members meeting (workshop) | 2 hours x 3 members | 2 hours x 3 members | 3 hours x $25 per member = 2 x $75 | 150
1.3 | Progress report meeting | Team members meeting (workshop) | 2 hours x 4 members | 2 hours x 4 members | 2 hours x $25 per member = 2 x $100 | 200
2 | Planning - Prepare meeting | Team members meeting (workshop) | 2 hours x 4 members | 2 hours x 4 members | 2 hours x $25 per member = 2 x $100 | 200
2.1 | Gantt Chart | Man Hours | 2 hours x 1 member | 2 hours x 1 member + 1 hour x 1 member | 2 hours x $25 per member = 2 x $25 + 1 hour x $25 per member = $75 | 75
2.2 | Stakeholder Register GitHub | Man Hours | 2 hours x 1 member | 1 hour x 1 member | 1 hour x $25 per member = 1 x $25 | 25
2.3 | Resource Requirement List | Man Hours | 2 hours x 1 member | 1 hour x 2 members | 1 hour x $25 per member = 1 x $50 | 50
2.4 | Review / Test changes/readme | Man Hours
2.5 | Progress report meeting | Team members meeting (workshop) | 2 hours x 4 members | 1 hour x 4 members | 1 hour x $25 per member = 1 x $100 | 100
3.1 | Design a website
Total Cost | [5 empty] | 5621.68