## Sheet1
When: 23/05/2024 14:15 PM |  | Who: Krillin Group (Alex, Luan, Anthony, Hunter) | Application: Timups Smart Watches
Note: please make sure you fill all information related to your project below and convert/include link to Wiki Or readme.md (GitHub)
ID | Scenario Title | Status | Scenario | Remarks
1 | Startup page | Pass | Main screen displays, can scroll and click most links | As expected
2 | Contact Us button in the main content | Fail | Pressing the Contact Us button (in the main content) should work | Button does nothing
3 | Nav Menu Buttons | Pass | Home, Watches, About, Contact Us, Orders buttons should work | As expected
4 | Log in, cart, and search buttons | Fail | Log in, cart, and search buttons in the top right should lead to their respective pages | Buttons do nothing
5 | Three dots that horizontally scroll | Pass | Pressing these buttons should scroll the horizontal advertisements | As expected
6 | Specific watch button | Fail | Clicking on watch should take you to that watches page | Button takes you back to the top of the page
7 | View all button | Fail | Clicking on view all should take you to a bigger page for all products | Button takes you back to the top of the page
8 | About us read more button | Fail | Clicking here should take you to the about.html page | Button takes you back to the top of the page
9 | Features Of Our Watches Read More | Fail | Clicking here should give more information | Button takes you back to the top of the page
10 | Orders page links | Fail | Every link ("Buy it Again", "Request a Return", "Track Shipment" and "View Order", etc…) should work | Every single button refreshes the page
11 | Contact Us requires email | Pass | Contact Us should check if user entered email | As expected
12 | "Reach at" contact footer buttons | Fail | Location, phone number, and demo@gmail should all link somewhere | Button links back to whatever page you're already on
13 | "About" social media buttons | Fail | Facebook, Twitter, Linkedin, and Instagram buttons should link to their respective sites | Button it links back to whatever page you're already on
14
15