## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
Krillin
Company name | Krillin |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Group Lead | Luan
Project Start Date: | 2024-02-19 |  |  |  |  | April | [13 empty] | May | [34 empty] | June
Scrolling Increment: | 60 | time axis 2024-04-19 to 2024-06-13
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-04-19 to 2024-06-13
Iteration 1
Finish Progress Report | Goal | Group | 100% | 2024-03-18 | 9
Create Stakeholder Register | Low Risk | Group | 100% | 2024-02-21 | 14
Create Personas | Low Risk | Luan & Alex | 100% | 2024-03-06 | 2
Test Personas | Med Risk | Hunter & Anthony | 100% | 2024-03-08 | 5
Write Group Meeting Report | Milestone | Group | 100% | 2024-03-13 | 5
Iteration 2
Finish Progress Report | Goal | Luan | 100% | 2024-04-27 | 7 | 2024-04-27: 2; 2024-04-28: 2; 2024-04-29: 2; 2024-04-30: 2; 2024-05-01: 2; 2024-05-02: 2; 2024-05-03: 2
Set Up Gantt Chart | Med Risk | Anthony | 100% | 2024-04-03 | 10
Create Resource Requirement List | Low Risk | Hunter | 100% | 2024-03-27 | 20
Create GitHub Boards | High Risk | Alex | 100% | 2024-04-02 | 19
Write Group Meeting Report | Milestone | Luan | 100% | 2024-04-13 | 14 | bar: 2024-04-19 to 2024-04-26
Iteration 3
Finish Progress Report | Goal | Luan | 100% | 2024-05-20 | 5 | 2024-05-20: 2; 2024-05-21: 2; 2024-05-22: 2; 2024-05-23: 2; 2024-05-24: 2
Finalize GitHub | High Risk | Alex | 100% | 2024-05-04 | 20
Finalize Gantt Chart | Med Risk | Anthony | 100% | 2024-05-04 | 20
Complete Risk Register | High Risk | Hunter | 100% | 2024-05-08 | 7
Fill in User Acceptence Testing | Low Risk | Group | 100% | 2024-05-22 | 2
Write Group Meeting Report | Milestone | Luan | 100% | 2024-05-15 | 10 | bar: 2024-05-15 to 2024-05-24
TITLE 4
Task 1 |  |  |  |  | 15
Task 2 |  |  |  |  | 5
Task 3 | Milestone |  |  |  | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-05-29 |  |  |  |  | May | [6 empty] | June | [27 empty] | July
Scrolling Increment: | 1 | time axis 2024-05-30 to 2024-07-24
Milestone description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-29 | 3 | T: 2; F: 2
Task 2 | Milestone |  |  | 2024-06-03 | 1 | bar: M
Task 3 | Low Risk |  | 50% | 2024-05-26 | 10
Task 4 | Milestone |  |  | 2024-06-18 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2024-06-04 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-06-04 | 13
Task 2 | On Track |  | 50% | 2024-06-06 | 9
Task 3 | Low Risk |  | 33% | 2024-06-11 | 11
Task 4 | Milestone |  |  | 2024-06-13 | 1 | bar: T
Task 5 |  |  |  | 2024-06-14 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-06-13 | 4
Task 2 | Med Risk |  |  | 2024-06-16 | 14
Task 3 | On Track |  |  | 2024-07-01 | 6
Task 4 | Goal |  |  | 2024-07-05 | 3 | F: 2; S: 2; S: 2
Task 5 | Low Risk |  |  | 2024-06-04 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-08 | 15
Task 2 |  |  |  | 2024-07-22 | 5
Task 3 | Milestone |  |  | 2024-09-02 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-05-29 |  |  |  |  | June | [27 empty] | July
Scrolling Increment: | 5 | time axis 2024-06-03 to 2024-07-28
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-06-03 to 2024-07-28
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-29 | 3
Task 2 | Milestone |  |  | 2024-06-03 | 1 | bar: 2024-06-03
Task 3 | Low Risk |  | 50% | 2024-05-26 | 10
Task 4 | Milestone |  |  | 2024-06-18 | 1 | bar: 2024-06-18
Task 5 | Med Risk |  | 10% | 2024-06-04 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-06-04 | 13
Task 2 | On Track |  | 50% | 2024-06-06 | 9
Task 3 | Low Risk |  | 33% | 2024-06-11 | 11
Task 4 | Milestone |  |  | 2024-06-13 | 1 | bar: 2024-06-13
Task 5 |  |  |  | 2024-06-14 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-06-13 | 4
Task 2 | Med Risk |  |  | 2024-06-16 | 14
Task 3 | On Track |  |  | 2024-07-01 | 6
Task 4 | Goal |  |  | 2024-07-05 | 3 | 2024-07-05: 2; 2024-07-06: 2; 2024-07-07: 2
Task 5 | Low Risk |  |  | 2024-06-04 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-08 | 15
Task 2 |  |  |  | 2024-07-22 | 5
Task 3 | Milestone |  |  | 2024-09-02 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one